## Budget Breakdown
| WBS Code | Activity | Estimation Defined | Cost per Unit | Cost per Hour | Hours/Units | Total Cost | Type of Expense
Site | 1.1 | Develop a course map | Hours for Event Coordinator to map the course | NA | $15.83/hour | 80 | 1266.4 | Operations
| 1.1.1 | Create a site plan | Hours for Event Coordinator to create a site map | NA | $15.83/hour | 40 | 633.2 | Operations
| 1.1.2 | Create a traffic control plan | Hours for Event Coordinator to devise a traffic plan | NA | $15.83/hour | 40 | 633.2 | Operations
| 1.1.3 | Schedule road closures and secure signage | Hours for Event Coordinator to create a schedule and secure signage and permissions for road closures | NA | $15.83/hour | 40 | 633.2 | Operations
| 1.1.4 | Do a test run | Hours for Event Assistants (2) to walk the path to ensure that the terrain is safe | NA | $14.08/hour | 40 | 1126.4 | Operations
| 1.1.5 | Mark booth locations | Hours for Event Assistants (2) to measure and mark vendor spaces; cost for tape and measuring tools | 15 | $14.08/hour | 2020-04-01 | 127.64 | Operations
| 1.1.6 | Coordinate installation of temporary accessibility ramps | Accessibility ramp quote from Amramp | 850 | NA | 4 | 3400 | Operations
| 1.2.1 | Acquire all necessary insurance documents | Cost for event application and liability insurance, along with hours for Event Organizer to obtain them | 1000 | $22.23/hour | 8 | 1177.84 | Operations
| 1.2.2 | Acquire necessary licenses and permits | Cost and Event Organizer hours for the permits/permissions from the City of Fort Worth | 1500 | $22.23/hour | 80 | 3278.4 | Operations
| 1.2.3 | Submit Outdoor Events Application | Hours for Event Organizer to submit an Outdoor Events Application | NA | $22.23/hour | 8 | 177.84 | Operations
| 1.2.4 | Make information packets | Hours for Event Assistant to print and create information packets for staff; quote from UPS ($0.10 per page X 20 pages X 25 staff) | 50 | $14.08/hour | 40 | 613.2 | Operations
| 1.3.1 | Rent generators | Cost to rent a generator and power accessories from rentalstops.com | 600 | NA | NA | 600 | Operations
| 1.3.2 | Electrical system and stage inspection | Inspection for electrical system and stage from the City of Fort Worth | 200 | NA | NA | 200 | Operations
| 1.4.1 | Rent essentials for site | Hours for Event Coordinator to schedule rentals | NA | $15.83/hour | 80 | 1266.4 | Operations
| 1.4.2 | Set up equipment rentals | Hours for Event Assistants (4) to set up trash and recycling bins, tents, tables, and chairs | NA | $14.08/hour | 16 | 901.12 | Operations
| 1.5.1 | Rent and install the stage and light towers | Cost for stage and light rentals; quote from moorerental.com | 650 | NA | NA | 650 | Operations
| 1.5.2 | PA system rental | PA system rental estimate; hours required by sound team for sound checks | 600 | $19.00/hour | 8 | 752 | Operations
[6 empty] | Estimated Site Related Costs |  | 17436.84
Personnel | WBS Code | Activity | Estimation Defined | Cost per Unit | Cost per Hour | Hours/Units | Total Cost | Type of Expense
| 2.1.1,2.1.2 | Approach previous/new Sponsors. | Hours spent by event coordinators to meet sponsers, plan strategies, set up virtual meetings with the sponsors, and race directors. Only virtual meetings so no travel cost included. Event Coordinators: 2 Each: $7598.40 Race Directors are from NTFB so no fee is included. Source: https://www.eventmanagerblog.com/event-planner-salary | NA | 15.83 | 480 | 15196.8 | Operations
| 2.1.1,2.1.2,2.3.3 | Prepare legal documentation for sponsors and vendors | A flalt fee/fixed fee is charged by attorneys for preparing legal documentation i.e. creating contract papers/legal services for the whole event. Estimation is made from online websites. Attorneys: 2 Each : $650 Source: Look for "Contractor Agreement Template" section in Link: https://neilgreenbaumlaw.com/packages-and-fees/ | NA | NA | NA | 1300 | Operations
| 2.2.1 | Draft budget | Hours spent by financial advisor for drafting initial, final, auditing, and budget analysis. Estimated from average hourly pay charged by financial advisors. Financial Advisor: 1 Source: https://www.ziprecruiter.com/Salaries/How-Much-Does-a-Financial-Advisor-Make-an-Hour | NA | 34 | 160 | 5440 | Operations
| 2.2.2 | Recruit additional staff for setting up race committee | Hours spent by NTFB board members to recruit additionoal resouces like Event Planners, Event Organizers, Event Coordinators etc. Only NTFB board members and volunteers would spend time on hiring additional staff. So, no fee is included. | NA | 0 | 480 | 0 | Operations
| 2.2.3 | Assign roles and responsibilities | Hours spent by Event planners for assigning tasks to the respective personnel for a specific area for the event. Event Planners: 2 Each: $7680 https://www.ziprecruiter.com/Salaries/How-Much-Does-an-Event-Planner-Make-an-Hour | NA | 24 | 320 | 15360 | Operations
| 2.2.4 | Create tasks and timelines | Hours spent by Event Planners/Organziers for drafting specific tasks, timelines and event milestones. Event Organizers: 1 Each: $11520 Additional volunteers would also work. Source: Same as above | NA | 24 | 480 | 11520 | Operations
| 2.2.5 | Oversee registration | Hours spent by volunteeers for answering questions from potential participants, provide administrative support, help with registration fee payments, prepare participant package to mail out or for pick up. Event Volunteers: 50 No fee charged as they are doing (part-time) for a social cause. Each volunteer would work for a scheduled time for alternative week. | NA | 0 | 1280 | 0 | Operations
| 2.3.1 | Make arrangements for conducting Expo | Booking a convention center for conducting expo. Convention center avg cost in denton. Source: https://www.eventective.com/denton-tx/meeting-venues/ | NA | NA | NA | 3500 | NA
| 2.3.1 | Expo vendor arrangements | Renting tables, chairs, tents for vendor booth setup during expo. Same items will be used during the marathon. Refer WBS 4.2.2 for excat cost breakdown for tables + chairs + tents (828 + 248 + 4250) | NA | NA | NA | 5326 | Operations
| 2.3.2 | Shortlist vendors | A panel of experts receiving the applications, reviewing, and selecting appropriate vendors. NTFB board members and volunteers will do the shortling from the applications. So, no cost included. | NA | 0 | 320 | 0 | Operations
| 2.4.1 | Collaborate and coordinate with third party labor workers | Third party labor workers for installing stages, barricades, archways a day before marathon. 10 Labor workers: Each $480.00 Source: ziprecruiter.com | NA | 12 | 40 | 4800 | Operations
| 2.4.2 | After marathon schedule | Hours spent by Event Coordinators for preparing after marathn schedule for marathon clean up, dispersing volunteers. Event Coordinators: 2 Each: $800.00 Source: ziprecruiter.com | NA | 20 | 40 | 1600 | Operations
| 2.4.3 | Contact and contract videography/photograpy | Fixed fee charged for filming for livestreaming on Internet,/TV; Photography service for website. Source: https://www.thumbtack.com/p/videography-prices | NA | NA | NA | 1000 | Operations
[6 empty] | Estimated Management Related Costs |  | 65042.8
Marketing | WBS Code | Activity | Estimation Defined | Cost per Unit | Cost per Hour | Hours/Units | Total Cost | Type of Expense
| 3.1.1 | Create and promote website | Cost of URL through GoDaddy | 12 |  |  | 12 | Capital
| 3.1.1 | Create and promote website | Cost of hosting/server space through GoDaddy | 120 |  |  | 120 | Capital
| 3.1.1 | Create and promote website | Cost of website development using an outside vendor OR | 7500 |  |  | 7500 | Operations
| 3.1.1 | Create and promote website | Hours of time for website development if staffer is hired |  | 75 | 50 | 3750 | Operations
| 3.2.1 | Create and order print pieces | Creation of logo by graphic designer | 300 |  |  | 300 | Operations
| 3.2.1 | Create and order print pieces | Creation of flyers, posters and banners, as well as mile markers for race path, using outside vendor OR | 1000 |  |  | 1000 | Operations
| 3.2.1 | Create and order print pieces | Hours of time for graphic design if staffer is hired |  | 75 | 20 | 1500 | Operations
| 3.2.1 | Create and order print pieces | Printing costs
| 3.2.1 | Create and order print pieces | Flyers from Vistaprint | 0.17 |  | 1000 | 170 | Operations
| 3.2.1 | Create and order print pieces | Posters from Vistaprint | 1.925 |  | 200 | 385 | Operations
| 3.2.1 | Create and order print pieces | Banners from Vistaprint | 130 |  | 50 | 6500 | Operations
| 3.2.1 | Create and order print pieces | Mile markers from Vistaprint (includes hardware) | 500 |  | 26 | 13000 | Operations
| 3.2.2 | Distribute print pieces | Postage to mail flyers to sponsors via USPS. | 2.8 |  | 200 | 560 | Operations
| 3.2.2 | Distribute print pieces | Time to take flyers, maps and traffic plans to local businesses and residents |  | 20 | 20 | 400 | Operations
| 3.3.1 | Create radio and TV spots | Production of radio spots, including writing the scripts. | 500 |  |  | 500 | Operations
| 3.3.1 | Create radio and TV spots | Production of TV spot, including the writing of the script, talent and all post-production. | 10000 |  |  | 10000 | Operations
| 3.3.2 | Buy air time to distribute advertising | Buying air time for radio spots for 5 months | 35000 |  |  | 35000 | Operations
| 3.3.2 | Buy air time to distribute advertising | Buying air time for TV spots for 5 months | 50000 |  |  | 50000 | Operations
| 3.4.1 | Create social media accounts | Staff member signs up for accounts on Facebook, Twitter and Instagram. Cost is one hour of labor. |  | 40 | 1 | 40 | Operations
| 3.4.2 | Create and post content on social media accounts | Write 6-10 blog posts to host on website and promote via social media, hiring a freelancer or outside vendor OR | 1000 |  |  | 1000 | Operations
| 3.4.2 | Create and post content on social media accounts | Creation of blog posts by staffer, in hours of time. |  | 40 | 25 | 1000 | Operations
| 3.4.2 | Create and post content on social media accounts | Schedule social media posts, when done by outside vendor, for 6 months OR | 3000 |  |  | 3000 | Operations
| 3.4.2 | Create and post content on social media accounts | Schedule social media posts, when done by staffer, for 6 months. |  | 20 | 90 | 1800 | Operations
| 3.5.1 | Create and order merchandise | Merchandise costs
| 3.5.1 | Create and order merchandise | T-shirts (5,000 each of S, M, L, XL) from 4Imprint | 3.85 |  | 20000 | 77000 | Operations
| 3.5.1 | Create and order merchandise | Key chains from 4Imprint | 0.72 |  | 20000 | 14400 | Operations
| 3.5.1 | Create and order merchandise | Water bottles ($ per bottle plus $150 set-up fee) from 4Imprint | 3.55 |  | 20000 | 71150 | Operations
| 3.5.1 | Create and order merchandise | Boxes for mailing merch from Staples (pkg = 25 boxes) | 5.5 |  | 800 | 4400 | Operations
| 3.5.1 | Create and order merchandise | Having agency place orders for merchandise OR | 1500 |  |  | 1500 | Operations
| 3.5.1 | Create and order merchandise | Having staffer place these orders and monitor them. |  | 20 | 5 | 100 | Operations
| 3.5.2 | Mail merchandise to runners | Postage via USPS (cheaper than UPS) for 20,000 registrants | 8 |  | 20000 | 160000 | Operations
[5 empty] | Total marketing costs using only vendors OR |  |  | 457937
[5 empty] | Total marketing costs using vendors and staffers |  |  | 452087
Spectator Activities | WBS Code | Activity | Estimation Defined | Cost per Unit | Cost per Hour | Hours/Units | Total Cost | Type of Expense
| 4.1.1 | DJ | Provide music entertainment for runners and spectators. Estimate from DJ Bogey on bark.com |  | 156.25 | 8 | 1250 | Operating expense
| 4.2.1 | Face Painting | Area for spectators/supporters to create signs and posters or do face painting with volunteer staff members |  | 0 | 4 | 0 | Operating expense
| 4.2.2 | MC -1 | Game led by MC during the race where spectators/supporters answer questions for prizes |  | 0 | 2 | 0 | Operating expense
|  | MC-2 | Welcome opening and Award Ceremony lead by NTRB staff |  | 0 | 2 | 0 | Operating expense
|  | Tables | 8' long tables, two to each tent; $9 each for rental (Taylor's Rental Equipment) | 9 |  | 92 | 828 | Operating expense
|  | Chairs | Prices and rate provded by Taylors Rentals. Equipment to be place on course and in Start/Finish area. Each tent will have two tables and two chairs; (Taylor's Rental Equipment) | 1.35 |  | 184 | 248.4 | Operating expense
|  | Tents | Estimates from Taylor's Rentals for 10 x 10 | 125 |  | 34 | 4250 | Operating expense
|  | Tents | Estimates from Taylor's Rentals for 20X20 | 300 |  | 2 | 600 | Operating expense
|  | EquipmentService | Estimate from Taylor's Rentals for roundtrip Delivery, Setup, and Breakdown on Sunday | 600 |  | 1 | 600 | Operating expense
|  | Portable Bathrooms | Estimate from Porto Potty Pro. includes roundtrip delivery | 140 |  | 50 | 7000 | Operating expense
|  | Hand sanitizer | Superfy hand sanitizer Gel 0.5 Gallon refill with Pump, Big Bulk 70% Alcohol based Hand Washer 68fl oz, W/refill bottle from Amazon | 30 |  | 55 | 1650 | Operating expense
|  | Face paint | 12 pack of Easy Face Paint Sticks from Amazon | 13 |  | 500 | 6500 | Operating expense
|  | Banner paper | Kraft Paper Roll 24'' X 1800'' (150ft) Brown,Black, and White Mega Roll - Made in Usa 100% Natural Recycled Material from Amazon | 20 |  | 540 | 10800 | Operating expense
|  | Markers | Sharpie 38250PP Permanent Markers, Chisel Tip, Assorted Colors, 8-Count, Standard Packaging from Amazon | 7 |  | 300 | 2100 | Operating expense
|  | Trivia cash prizes | Three winners: 1st - $250, 2nd - $100, 3rd - $50 | 400 |  | 1 | 400 | Operating expense
|  | Trophies | Estimate from CrownAwards.com; Trophies to 5 top finishers | 100 |  | 5 | 500 | Operating expense
|  | Medals | Estimate from CrownAwards.com.; Finishers within time limit | 3 |  | 1500 | 4500 | Operating expense
|  | Certificates | Estimate from CrownAwards.com.; Sold in quantities of 10 for $3.90 | 3.9 |  | 200 | 780 | Operating expense
|  | Cash Prizes for Top Five Finishers | Estimate based on Management, Sponsors, and NTFB | 44000 |  | 1 | 44000 | Operating expense
[5 empty] | Estimated Spectator Activity Costs |  |  | 86006.4
Safety & Risk Management | WBS Code | Activity | Estimation Defined | Cost per Unit | Cost per Hour | Hours/Units | Type of Expense | Total Cost
| 5.1.1 | Assign medical team to follow runners to handle medical emergencies and set up mobile hospitals at appropriate intervals. | Mobile hospitals include chairs, tents, first air kits. Chair, tents and tables costing up to: $550 First aid kit: $54.70 Average cost altogether estimated: $600 per mobile hospital https://fortworthtexas.gov/fire/ems-standby/ | 600 |  | 26 | Operating Expenses | 15600
| 5.1.2 | Contract Event Paramedic Services | Hours allocated to finalize contracts for emergency medical support with ambulance vehicles on site |  | 300 | 10 | Operating Expenses | 3000
| 5.2.1 | Create Emergency Information Maps | Emergency maps to be printed | 2.26 |  | 1000 | Operating Expenses | 2260
| 5.3.1 | Employ Event Security Services | Hours allocated to hire special security persons and also contacting local emergency services https://fortworthtexas.gov/fire/ems-standby/ |  | 22 | 320 | Operating Expenses | 7040
| 5.3.2 | Rental CC TV installation | Third party contracts, cc tv - 20 cameras each 150 https://www.sunbeltrentals.com/equipment/items/1645/surveillance-equipment/ |  | 150 | 20 | Operating Expenses | 3000
[5 empty] | Estimated Security Costs |  |  | 30900